## Sheet1
Project ID | Project Name | Project Type | Project City | Project State | Task ID | Task Name | Start Date | End Date | Planned End Date | Status | Delay Reason | Delay Type
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10001 | Project Kickoff | 2023-01-01 | 2023-01-02 | 2023-01-02 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10002 | Site Survey | 2023-01-03 | 2023-01-11 | 2023-01-09 | Delayed | Weather Conditions | Material
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10003 | Feasibility Study | 2023-01-12 | 2023-01-20 | 2023-01-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10004 | Design Phase 1 | 2023-01-21 | 2023-02-10 | 2023-02-08 | Delayed | Resource Availability | Men
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10005 | Design Phase 2 | 2023-02-11 | 2023-02-28 | 2023-02-28 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10006 | Procurement Planning | 2023-03-01 | 2023-03-10 | 2023-03-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10007 | Vendor Selection | 2023-03-11 | 2023-03-20 | 2023-03-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10008 | Order Placement | 2023-03-21 | 2023-03-25 | 2023-03-25 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10009 | Initial Site Preparation | 2023-03-26 | 2023-04-05 | 2023-04-05 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10010 | Equipment Delivery | 2023-04-06 | 2023-04-16 | 2023-04-14 | Delayed | Logistic Issues | Material
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10011 | Foundation Work | 2023-04-17 | 2023-04-30 | 2023-04-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10012 | Structural Steel Erection | 2023-05-01 | 2023-05-20 | 2023-05-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10013 | Mechanical Installation | 2023-05-21 | 2023-06-10 | 2023-06-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10014 | Electrical Installation | 2023-06-11 | 2023-06-30 | 2023-06-29 | Delayed | Material Shortage | Material
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10015 | Piping Installation | 2023-07-01 | 2023-07-20 | 2023-07-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10016 | HVAC Installation | 2023-07-21 | 2023-07-30 | 2023-07-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10017 | Instrumentation Installation | 2023-07-31 | 2023-08-10 | 2023-08-09 | Delayed | Technical Issues | Machinery
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10018 | Insulation and Painting | 2023-08-11 | 2023-08-20 | 2023-08-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10019 | Pre-commissioning Activities | 2023-08-21 | 2023-08-30 | 2023-08-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10020 | Commissioning Phase 1 | 2023-09-01 | 2023-09-10 | 2023-09-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10021 | Commissioning Phase 2 | 2023-09-11 | 2023-09-20 | 2023-09-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10022 | Final Inspection | 2023-09-21 | 2023-09-25 | 2023-09-25 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10023 | Project Handover Preparation | 2023-09-26 | 2023-09-30 | 2023-09-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10024 | Project Handover | 2023-10-01 | 2023-10-05 | 2023-10-05 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10025 | Site Demobilization | 2023-10-06 | 2023-10-10 | 2023-10-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10026 | Landscaping | 2023-10-11 | 2023-10-20 | 2023-10-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10027 | Final Documentation | 2023-10-21 | 2023-10-30 | 2023-10-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10028 | Safety Training | 2023-11-01 | 2023-11-05 | 2023-11-05 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10029 | Operational Training | 2023-11-06 | 2023-11-15 | 2023-11-15 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10030 | Equipment Testing | 2023-11-16 | 2023-11-25 | 2023-11-25 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10031 | System Integration Testing | 2023-11-26 | 2023-12-05 | 2023-12-05 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10032 | Quality Assurance | 2023-12-06 | 2023-12-15 | 2023-12-15 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10033 | Regulatory Compliance Check | 2023-12-16 | 2023-12-20 | 2023-12-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10034 | Risk Assessment | 2023-12-21 | 2023-12-25 | 2023-12-25 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10035 | Final Adjustments | 2023-12-26 | 2023-12-30 | 2023-12-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10036 | Post-implementation Review | 2024-01-02 | 2024-01-05 | 2024-01-05 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10037 | Stakeholder Meeting | 2024-01-06 | 2024-01-07 | 2024-01-07 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10038 | Feedback Collection | 2024-01-08 | 2024-01-10 | 2024-01-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10039 | Process Improvement Planning | 2024-01-11 | 2024-01-15 | 2024-01-15 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10040 | Implementation of Improvements | 2024-01-16 | 2024-01-25 | 2024-01-25 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10041 | Maintenance Schedule Setup | 2024-01-26 | 2024-01-30 | 2024-01-30 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10042 | Regular Maintenance | 2024-02-01 | 2024-02-10 | 2024-02-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10043 | Performance Review | 2024-02-11 | 2024-02-15 | 2024-02-15 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10044 | Final Report Preparation | 2024-02-16 | 2024-02-20 | 2024-02-20 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10045 | Submission to Authorities | 2024-02-21 | 2024-02-22 | 2024-02-22 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10046 | Regulatory Approval | 2024-02-23 | 2024-02-28 | 2024-02-28 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10047 | Project Closeout | 2024-03-01 | 2024-03-05 | 2024-03-05 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10048 | Knowledge Transfer | 2024-03-06 | 2024-03-10 | 2024-03-10 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10049 | Archiving Documents | 2024-03-11 | 2024-03-15 | 2024-03-15 | On Time
1 | Refinery Expansion Project | Oil and Gas Refinery | Mumbai | Maharashtra | 10050 | Final Audit | 2024-03-16 | 2024-03-20 | 2024-03-20 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20001 | Project Initiation | 2022-08-01 | 2024-02-01 | 2024-02-01 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20002 | Feasibility Study | 2022-08-02 | 2024-02-15 | 2024-02-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20003 | Environmental Impact Assessment | 2022-08-03 | 2024-03-01 | 2024-03-01 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20004 | Permitting | 2022-08-04 | 2024-03-15 | 2024-03-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20005 | Land Acquisition | 2022-08-05 | 2024-03-31 | 2024-03-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20006 | Detailed Engineering Design | 2022-08-06 | 2024-04-15 | 2024-04-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20007 | Equipment Procurement | 2022-08-07 | 2024-05-01 | 2024-05-01 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20008 | Construction | 2022-08-08 | 2024-05-15 | 2024-05-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20009 | Installation | 2022-08-09 | 2024-05-31 | 2024-05-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20010 | Testing and Commissioning | 2022-08-10 | 2024-06-15 | 2024-06-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20011 | Performance Testing | 2022-08-11 | 2024-06-30 | 2024-06-30 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20012 | Quality Assurance | 2022-08-12 | 2024-07-15 | 2024-07-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20013 | Safety Audit | 2022-08-13 | 2024-07-31 | 2024-07-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20014 | Regulatory Compliance | 2022-08-14 | 2024-08-15 | 2024-08-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20015 | Final Inspections | 2022-08-15 | 2024-08-31 | 2024-08-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20016 | Handover | 2022-08-16 | 2024-09-15 | 2024-09-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20017 | Project Closeout | 2022-08-17 | 2024-09-30 | 2024-09-30 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20018 | Documentation | 2022-08-18 | 2024-10-15 | 2024-10-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20019 | Knowledge Transfer | 2022-08-19 | 2024-10-31 | 2024-10-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20020 | Project Evaluation | 2022-08-20 | 2024-11-15 | 2024-11-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20021 | Performance Review | 2022-08-21 | 2024-11-30 | 2024-11-30 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20022 | Closure | 2022-08-22 | 2024-12-15 | 2024-12-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20023 | Final Audit | 2022-08-23 | 2024-12-31 | 2024-12-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20024 | Project Signoff | 2022-08-24 | 2025-01-15 | 2025-01-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20025 | Post-Project Review | 2022-08-25 | 2025-01-31 | 2025-01-31 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20026 | Lessons Learned | 2022-08-26 | 2025-02-15 | 2025-02-15 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20027 | Project Wrap-up | 2022-08-27 | 2025-02-28 | 2025-02-28 | On Time
2 | Barmar Refinery Project | Oil and Gas Refinery | Barmar | Rajasthan | 20028 | Final Report | 2022-08-28 | 2025-08-28 | 2025-08-28 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30001 | Project Initiation | 2022-10-01 | 2022-12-15 | 2022-11-30 | Delayed | Legal documentation delay | Men
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30002 | Feasibility Study | 2022-10-05 | 2023-01-05 | 2022-12-10 | Delayed | Environmental study delay | Material
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30003 | Environmental Impact Assessment | 2022-10-10 | 2023-01-10 | 2022-12-20 | Delayed | Regulatory approval delay | Material
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30004 | Land Acquisition | 2022-10-15 | 2023-01-15 | 2022-12-30 | Delayed | Land negotiation delay | Material
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30005 | Geological Survey | 2022-10-20 | 2023-01-20 | 2023-01-05 | Delayed | Regulatory approval delay | Material
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30006 | Permitting | 2022-10-25 | 2023-01-10 | 2023-01-10 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30007 | Detailed Engineering Design | 2022-11-01 | 2023-01-15 | 2023-01-15 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30008 | Equipment Procurement | 2022-11-05 | 2023-01-20 | 2023-01-20 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30009 | Site Preparation | 2022-11-10 | 2023-01-25 | 2023-01-25 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30010 | Construction | 2022-11-15 | 2023-02-05 | 2023-02-05 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30011 | Installation | 2022-11-20 | 2023-02-10 | 2023-02-10 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30012 | Testing and Commissioning | 2022-11-25 | 2023-02-15 | 2023-02-15 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30013 | Performance Testing | 2022-12-01 | 2023-02-20 | 2023-02-20 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30014 | Quality Assurance | 2022-12-05 | 2023-03-01 | 2023-03-01 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30015 | Safety Audit | 2022-12-10 | 2023-03-05 | 2023-03-05 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30016 | Regulatory Compliance | 2022-12-15 | 2023-03-10 | 2023-03-10 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30017 | Final Inspections | 2022-12-20 | 2023-03-15 | 2023-03-15 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30018 | Handover | 2022-12-25 | 2023-03-20 | 2023-03-20 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30019 | Project Closeout | 2022-12-30 | 2023-03-25 | 2023-03-25 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30020 | Documentation | 2023-01-05 | 2023-04-01 | 2023-04-01 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30021 | Project Review | 2023-01-10 | 2023-04-05 | 2023-04-05 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30022 | Lessons Learned | 2023-01-15 | 2023-04-10 | 2023-04-10 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30023 | Close Project | 2023-01-20 | 2023-04-15 | 2023-04-15 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30024 | Reporting | 2023-01-25 | 2023-04-20 | 2023-04-20 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30025 | Resource Allocation | 2023-02-01 | 2023-04-25 | 2023-04-25 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30026 | Stakeholder Management | 2023-02-05 | 2023-05-01 | 2023-05-01 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30027 | Risk Management | 2023-02-10 | 2023-05-05 | 2023-05-05 | On Time
3 | Ananthapur Mining Project | Mining and Mineral Processing | Ananthapur | Andhra Pradesh | 30028 | Final Report | 2023-02-10 | 2023-05-10 | 2023-05-15 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40001 | Project Kickoff | 2022-11-01 | 2022-11-02 | 2022-11-02 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40002 | Site Survey | 2022-11-03 | 2022-11-10 | 2022-11-09 | Delayed | Weather Conditions | Material
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40003 | Feasibility Study | 2022-11-11 | 2022-11-20 | 2022-11-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40004 | Design Phase 1 | 2022-11-21 | 2022-12-10 | 2022-12-08 | Delayed | Resource Availability | Men
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40005 | Design Phase 2 | 2022-12-11 | 2022-12-28 | 2022-12-28 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40006 | Procurement Planning | 2022-12-29 | 2023-01-08 | 2023-01-08 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40007 | Vendor Selection | 2023-01-09 | 2023-01-18 | 2023-01-18 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40008 | Order Placement | 2023-01-19 | 2023-01-25 | 2023-01-25 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40009 | Initial Site Preparation | 2023-01-26 | 2023-02-05 | 2023-02-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40010 | Equipment Delivery | 2023-02-06 | 2023-02-16 | 2023-02-14 | Delayed | Logistic Issues | Material
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40011 | Foundation Work | 2023-02-17 | 2023-02-28 | 2023-02-28 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40012 | Structural Steel Erection | 2023-03-01 | 2023-03-20 | 2023-03-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40013 | Mechanical Installation | 2023-03-21 | 2023-04-10 | 2023-04-10 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40014 | Electrical Installation | 2023-04-11 | 2023-04-30 | 2023-04-29 | Delayed | Material Shortage | Material
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40015 | Piping Installation | 2023-05-01 | 2023-05-20 | 2023-05-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40016 | HVAC Installation | 2023-05-21 | 2023-05-30 | 2023-05-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40017 | Instrumentation Installation | 2023-05-31 | 2023-06-10 | 2023-06-09 | Delayed | Technical Issues | Machinery
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40018 | Insulation and Painting | 2023-06-11 | 2023-06-20 | 2023-06-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40019 | Pre-commissioning Activities | 2023-06-21 | 2023-06-30 | 2023-06-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40020 | Commissioning Phase 1 | 2023-07-01 | 2023-07-10 | 2023-07-10 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40021 | Commissioning Phase 2 | 2023-07-11 | 2023-07-20 | 2023-07-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40022 | Final Inspection | 2023-07-21 | 2023-07-25 | 2023-07-25 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40023 | Project Handover Preparation | 2023-07-26 | 2023-07-30 | 2023-07-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40024 | Project Handover | 2023-07-31 | 2023-08-05 | 2023-08-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40025 | Site Demobilization | 2023-08-06 | 2023-08-10 | 2023-08-10 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40026 | Landscaping | 2023-08-11 | 2023-08-20 | 2023-08-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40027 | Final Documentation | 2023-08-21 | 2023-08-30 | 2023-08-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40028 | Safety Training | 2023-09-01 | 2023-09-05 | 2023-09-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40029 | Operational Training | 2023-09-06 | 2023-09-15 | 2023-09-15 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40030 | System Integration Testing | 2023-09-16 | 2023-09-25 | 2023-09-25 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40031 | Quality Assurance | 2023-09-26 | 2023-10-05 | 2023-10-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40032 | Regulatory Compliance Check | 2023-10-06 | 2023-10-10 | 2023-10-10 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40033 | Risk Assessment | 2023-10-11 | 2023-10-15 | 2023-10-15 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40034 | Final Adjustments | 2023-10-16 | 2023-10-20 | 2023-10-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40035 | Post-implementation Review | 2023-10-21 | 2023-10-25 | 2023-10-25 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40036 | Stakeholder Meeting | 2023-10-26 | 2023-10-27 | 2023-10-27 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40037 | Feedback Collection | 2023-10-28 | 2023-10-30 | 2023-10-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40038 | Process Improvement Planning | 2023-10-31 | 2023-11-05 | 2023-11-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40039 | Implementation of Improvements | 2023-11-06 | 2023-11-15 | 2023-11-15 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40040 | Maintenance Schedule Setup | 2023-11-16 | 2023-11-20 | 2023-11-20 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40041 | Regular Maintenance | 2023-11-21 | 2023-11-30 | 2023-11-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40042 | Performance Review | 2023-12-01 | 2023-12-05 | 2023-12-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40043 | Final Report Preparation | 2023-12-06 | 2023-12-10 | 2023-12-10 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40044 | Submission to Authorities | 2023-12-11 | 2023-12-12 | 2023-12-12 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40045 | Regulatory Approval | 2023-12-13 | 2023-12-18 | 2023-12-18 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40046 | Project Closeout | 2023-12-19 | 2023-12-23 | 2023-12-23 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40047 | Knowledge Transfer | 2023-12-24 | 2023-12-30 | 2023-12-30 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40048 | Archiving Documents | 2024-01-02 | 2024-01-05 | 2024-01-05 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40049 | Final Audit | 2024-01-06 | 2024-01-10 | 2024-01-10 | On Time
4 | Hazira Refinery Project | Oil and Gas Refinery | Hazira | Gujarat | 40050 | Project Completion | 2024-01-11 | 2024-01-15 | 2024-01-08 | Delayed | Overall Delays | Men/Material/Machinery
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60001 | Feasibility Study | 2022-01-01 | 2022-03-15 | 2022-02-28 | Delayed | Resource constraints | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60002 | Environmental Assessment | 2022-02-01 | 2022-04-01 | 2022-03-15 | Delayed | Regulatory approvals | Material
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60003 | Land Acquisition | 2022-03-01 | 2022-05-01 | 2022-04-15 | Delayed | Negotiation delays | Material
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60004 | Geological Survey | 2022-04-01 | 2022-04-30 | 2022-04-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60005 | Permitting | 2022-05-01 | 2022-05-31 | 2022-05-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60006 | Detailed Engineering Design | 2022-06-01 | 2022-06-30 | 2022-06-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60007 | Equipment Procurement | 2022-07-01 | 2022-07-31 | 2022-07-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60008 | Site Preparation | 2022-08-01 | 2022-08-31 | 2022-08-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60009 | Construction | 2022-09-01 | 2022-09-30 | 2022-09-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60010 | Installation | 2022-10-01 | 2022-10-31 | 2022-10-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60011 | Testing and Commissioning | 2022-11-01 | 2022-11-30 | 2022-11-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60012 | Performance Testing | 2022-12-01 | 2022-12-31 | 2022-12-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60013 | Quality Assurance | 2023-01-01 | 2023-01-31 | 2023-01-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60014 | Safety Audit | 2023-02-01 | 2023-02-28 | 2023-02-28 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60015 | Regulatory Compliance | 2023-03-01 | 2023-03-31 | 2023-03-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60016 | Final Inspections | 2023-04-01 | 2023-04-30 | 2023-04-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60017 | Handover | 2023-05-01 | 2023-05-31 | 2023-05-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60018 | Project Closeout | 2023-06-01 | 2023-06-30 | 2023-06-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60019 | Documentation | 2023-07-01 | 2023-07-31 | 2023-07-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60020 | Project Review | 2023-08-01 | 2023-08-31 | 2023-08-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60021 | Lessons Learned | 2023-09-01 | 2023-09-30 | 2023-09-30 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60022 | Close Project | 2023-12-01 | 2023-10-31 | 2023-10-31 | Delayed
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60023 | Reporting | 2023-12-01 | 2023-12-31 | 2023-12-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60024 | Resource Allocation | 2023-12-01 | 2023-12-31 | 2023-12-31 | On Time
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60025 | Stakeholder Management | 2023-12-15 | 2024-01-15 | 2024-01-01 | Delayed | Stakeholder conflicts | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60026 | Risk Management | 2024-01-15 | 2024-02-15 | 2024-02-01 | Delayed | Unexpected events | Material
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60027 | Change Management | 2024-02-15 | 2024-03-15 | 2024-03-01 | Delayed | Change in scope | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60028 | Project Audit | 2024-03-15 | 2024-04-15 | 2024-04-01 | Delayed | Audit issues | Material
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60029 | Lessons Learned Review | 2024-04-15 | 2024-05-15 | 2024-05-01 | Delayed | Additional findings | Machinery
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60030 | Documentation Review | 2024-05-15 | 2024-06-15 | 2024-06-01 | Delayed | Incomplete documents | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60031 | Final Reporting | 2024-06-15 | 2024-07-15 | 2024-07-01 | Delayed | Report finalization delay | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60032 | System Handover | 2024-07-15 | 2024-08-15 | 2024-08-01 | Delayed | System issues | Machinery
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60033 | Stakeholder Approval | 2024-08-15 | 2024-09-15 | 2024-09-01 | Delayed | Approval delays | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60034 | Final Closeout Meeting | 2024-09-15 | 2024-10-15 | 2024-10-01 | Delayed | Scheduling conflicts | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60035 | Project Archive | 2024-10-15 | 2024-11-15 | 2024-11-01 | Delayed | Archive issues | Material
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60036 | Final Sign-off | 2024-11-15 | 2024-12-15 | 2024-12-01 | Delayed | Final approval delay | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60037 | Performance Review | 2024-12-15 | 2025-01-15 | 2025-01-01 | Delayed | Review delays | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60038 | System Handover | 2025-01-15 | 2025-02-15 | 2025-02-01 | Delayed | System issues | Machinery
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60039 | Final Documentation | 2025-02-15 | 2025-03-15 | 2025-03-01 | Delayed | Document delays | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60040 | Final Approvals | 2025-03-15 | 2025-04-15 | 2025-04-01 | Delayed | Approval issues | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60041 | Stakeholder Meeting | 2025-04-15 | 2025-05-15 | 2025-05-01 | Delayed | Scheduling conflicts | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60042 | Final Walkthrough | 2025-05-15 | 2025-06-15 | 2025-06-01 | Delayed | Final review | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60043 | Final Sign-off | 2025-06-15 | 2025-07-15 | 2025-07-01 | Delayed | Approval delays | Men
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60044 | Project Closure | 2025-07-15 | 2025-08-15 | 2025-08-01 | Delayed | Closure issues | Material
6 | Ropar Mining Project | Mining and Mineral Processing | Ropar | Punjab | 60045 | Archive Project | 2025-08-15 | 2025-09-15 | 2025-09-01 | Delayed | Archive delays | Material
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70001 | Feasibility Study | 2021-12-01 | 2022-03-31 | 2022-03-31 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70002 | Environmental Assessment | 2022-01-01 | 2022-04-15 | 2022-04-15 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70003 | Land Acquisition | 2022-01-15 | 2022-05-01 | 2022-05-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70004 | Geological Survey | 2022-02-01 | 2022-06-01 | 2022-06-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70005 | Permitting | 2022-02-15 | 2022-06-30 | 2022-06-30 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70006 | Detailed Engineering Design | 2022-03-01 | 2022-08-15 | 2022-08-15 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70007 | Equipment Procurement | 2022-03-15 | 2022-09-01 | 2022-09-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70008 | Site Preparation | 2022-04-01 | 2022-10-01 | 2022-10-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70009 | Foundation Work | 2022-04-15 | 2022-11-01 | 2022-11-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70010 | Structural Work | 2022-05-01 | 2022-12-01 | 2022-12-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70011 | Electrical Work | 2022-05-15 | 2023-01-01 | 2023-01-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70012 | Piping Work | 2022-06-01 | 2023-02-01 | 2023-02-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70013 | HVAC Installation | 2022-06-15 | 2023-03-01 | 2023-03-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70014 | Safety Systems Installation | 2022-07-01 | 2023-04-01 | 2023-04-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70015 | Quality Control Inspection | 2022-07-15 | 2023-05-01 | 2023-05-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70016 | Testing & Commissioning | 2022-08-01 | 2023-06-01 | 2023-06-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70017 | Final Inspection | 2022-08-15 | 2023-07-01 | 2023-07-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70018 | Regulatory Approval | 2022-09-01 | 2023-08-01 | 2023-08-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70019 | Staff Training | 2022-09-15 | 2023-09-01 | 2023-09-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70020 | Operational Readiness Review | 2022-10-01 | 2023-10-01 | 2023-10-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70021 | Startup & Initial Operations | 2022-10-15 | 2023-11-01 | 2023-11-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70022 | Performance Monitoring | 2022-11-01 | 2023-12-01 | 2023-12-01 | On Time
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70023 | Project Handover | 2022-11-15 | 2024-01-01 | 2023-12-15 | Delayed | Late equipment delivery | Material
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70024 | Post-Implementation Review | 2022-12-01 | 2024-02-01 | 2024-01-15 | Delayed | Workforce shortage | Men
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70025 | Closeout & Documentation | 2022-12-15 | 2024-02-15 | 2024-01-31 | Delayed | Documentation delays | Men
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70026 | Demobilization | 2023-01-01 | 2024-02-28 | 2024-02-14 | Delayed | Site clearance issues | Machinery
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70027 | Site Restoration | 2023-01-15 | 2024-03-01 | 2024-02-15 | Delayed | Resource allocation | Men
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70028 | Final Audit | 2023-02-01 | 2024-03-15 | 2024-02-28 | Delayed | Audit rescheduling | Men
7 | Tarapur Nuclear Project | Nuclear Power Plant | Tarapur | Maharashtra | 70029 | Final Report | 2023-02-15 | 2024-03-31 | 2024-03-15 | Delayed | Report preparation
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80001 | Feasibility Study | 2017-09-01 | 2017-11-30 | 2017-11-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80002 | Environmental Assessment | 2017-10-01 | 2017-12-31 | 2017-12-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80003 | Land Acquisition | 2017-10-15 | 2018-01-15 | 2018-01-15 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80004 | Geological Survey | 2017-11-01 | 2018-02-28 | 2018-02-28 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80005 | Permitting | 2017-11-15 | 2018-03-15 | 2018-03-15 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80006 | Detailed Engineering Design | 2017-12-01 | 2018-04-30 | 2018-04-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80007 | Equipment Procurement | 2018-01-01 | 2018-05-31 | 2018-05-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80008 | Site Preparation | 2018-01-15 | 2018-06-30 | 2018-06-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80009 | Foundation Work | 2018-02-01 | 2018-07-31 | 2018-07-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80010 | Structural Work | 2018-02-15 | 2018-08-31 | 2018-08-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80011 | Electrical Work | 2018-03-01 | 2018-09-30 | 2018-09-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80012 | Piping Work | 2018-03-15 | 2018-10-31 | 2018-10-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80013 | HVAC Installation | 2018-04-01 | 2018-11-30 | 2018-11-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80014 | Safety Systems Installation | 2018-04-15 | 2018-12-31 | 2018-12-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80015 | Quality Control Inspection | 2018-05-01 | 2019-01-31 | 2019-01-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80016 | Testing & Commissioning | 2018-05-15 | 2019-02-28 | 2019-02-28 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80017 | Final Inspection | 2018-06-01 | 2019-03-31 | 2019-03-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80018 | Regulatory Approval | 2018-06-15 | 2019-04-30 | 2019-04-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80019 | Staff Training | 2018-07-01 | 2019-05-31 | 2019-05-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80020 | Operational Readiness Review | 2018-07-15 | 2019-06-30 | 2019-06-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80021 | Startup & Initial Operations | 2018-08-01 | 2019-07-31 | 2019-07-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80022 | Performance Monitoring | 2018-08-15 | 2019-08-31 | 2019-08-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80023 | Project Handover | 2018-09-01 | 2019-09-30 | 2019-09-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80024 | Post-Implementation Review | 2018-09-15 | 2019-10-31 | 2019-10-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80025 | Closeout & Documentation | 2018-10-01 | 2019-11-30 | 2019-11-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80026 | Demobilization | 2018-10-15 | 2019-12-31 | 2019-12-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80027 | Site Restoration | 2018-11-01 | 2020-01-31 | 2020-01-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80028 | Final Audit | 2018-11-15 | 2020-02-28 | 2020-02-28 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80029 | Final Report | 2018-12-01 | 2020-03-31 | 2020-03-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80030 | Operational Training | 2018-12-15 | 2020-04-30 | 2020-04-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80031 | O&M Manual Preparation | 2019-01-01 | 2020-05-31 | 2020-05-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80032 | Spare Parts Procurement | 2019-01-15 | 2020-06-30 | 2020-06-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80033 | Equipment Testing | 2019-02-01 | 2020-07-31 | 2020-07-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80034 | Safety Drills | 2019-02-15 | 2020-08-31 | 2020-08-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80035 | Waste Management Plan | 2019-03-01 | 2020-09-30 | 2020-09-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80036 | Contingency Planning | 2019-03-15 | 2020-10-31 | 2020-10-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80037 | Fire Safety Measures | 2019-04-01 | 2020-11-30 | 2020-11-30 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80038 | Emergency Response Plan | 2019-04-15 | 2020-12-31 | 2020-12-31 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80039 | Final Safety Review | 2019-05-01 | 2021-01-15 | 2021-01-15 | On Time
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80040 | Final Regulatory Review | 2019-05-15 | 2021-02-15 | 2021-01-31 | Delayed | Regulatory delay | Men
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80041 | Final Commissioning | 2019-06-01 | 2021-03-01 | 2021-02-15 | Delayed | Commissioning delay | Machinery
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80042 | Final Handing Over | 2019-06-15 | 2021-03-15 | 2021-02-28 | Delayed | Handover documentation | Men
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80043 | Final Operation Readiness | 2019-07-01 | 2021-03-31 | 2021-03-15 | Delayed | Readiness assessment | Men
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80044 | Final Project Closeout | 2019-07-15 | 2021-04-15 | 2021-03-31 | Delayed | Closeout delays | Men
8 | Kudankulam Nuclear Project | Nuclear Power Plant | Kudankulam | Tamil Nadu | 80045 | Final Report Submission | 2019-08-01 | 2021-04-30 | 2021-04-15 | Delayed | Report preparation delay | Men
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90001 | Feasibility Study | 2019-04-01 | 2019-07-15 | 2019-06-30 | Delayed | Extended review process | Men
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90002 | Environmental Assessment | 2019-05-01 | 2019-08-30 | 2019-08-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90003 | Land Acquisition | 2019-06-01 | 2019-09-30 | 2019-09-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90004 | Geological Survey | 2019-07-01 | 2019-11-30 | 2019-10-31 | Delayed | Equipment malfunction | Machinery
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90005 | Permitting | 2019-07-15 | 2019-12-31 | 2019-12-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90006 | Detailed Engineering Design | 2019-08-01 | 2020-01-31 | 2020-01-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90007 | Equipment Procurement | 2019-09-01 | 2020-03-31 | 2020-03-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90008 | Site Preparation | 2019-10-01 | 2020-04-30 | 2020-04-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90009 | Foundation Work | 2019-11-01 | 2020-05-31 | 2020-05-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90010 | Structural Work | 2019-12-01 | 2020-06-30 | 2020-06-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90011 | Electrical Work | 2020-01-01 | 2020-07-31 | 2020-07-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90012 | Piping Work | 2020-02-01 | 2020-08-31 | 2020-08-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90013 | HVAC Installation | 2020-03-01 | 2020-09-30 | 2020-09-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90014 | Safety Systems Installation | 2020-04-01 | 2020-10-31 | 2020-10-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90015 | Quality Control Inspection | 2020-05-01 | 2020-11-30 | 2020-11-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90016 | Testing & Commissioning | 2020-06-01 | 2020-12-31 | 2020-12-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90017 | Final Inspection | 2020-07-01 | 2021-01-31 | 2021-01-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90018 | Regulatory Approval | 2020-08-01 | 2021-02-28 | 2021-02-28 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90019 | Staff Training | 2020-09-01 | 2021-03-31 | 2021-03-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90020 | Operational Readiness Review | 2020-10-01 | 2021-04-30 | 2021-04-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90021 | Startup & Initial Operations | 2020-11-01 | 2021-05-31 | 2021-05-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90022 | Performance Monitoring | 2020-12-01 | 2021-06-30 | 2021-06-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90023 | Project Handover | 2021-01-01 | 2021-07-31 | 2021-07-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90024 | Post-Implementation Review | 2021-02-01 | 2021-08-31 | 2021-08-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90025 | Closeout & Documentation | 2021-03-01 | 2021-09-30 | 2021-09-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90026 | Demobilization | 2021-04-01 | 2021-10-31 | 2021-10-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90027 | Site Restoration | 2021-05-01 | 2021-11-30 | 2021-11-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90028 | Final Audit | 2021-06-01 | 2021-12-31 | 2021-12-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90029 | Final Report | 2021-07-01 | 2022-01-31 | 2022-01-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90030 | Operational Training | 2021-08-01 | 2022-02-28 | 2022-02-28 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90031 | O&M Manual Preparation | 2021-09-01 | 2022-03-31 | 2022-03-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90032 | Spare Parts Procurement | 2021-10-01 | 2022-04-30 | 2022-04-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90033 | Equipment Testing | 2021-11-01 | 2022-05-31 | 2022-05-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90034 | Safety Drills | 2021-12-01 | 2022-06-30 | 2022-06-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90035 | Waste Management Plan | 2022-01-01 | 2022-07-31 | 2022-07-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90036 | Contingency Planning | 2022-02-01 | 2022-08-31 | 2022-08-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90037 | Fire Safety Measures | 2022-03-01 | 2022-09-30 | 2022-09-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90038 | Emergency Response Plan | 2022-04-01 | 2022-10-31 | 2022-10-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90039 | Final Safety Review | 2022-05-01 | 2022-11-30 | 2022-11-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90040 | Final Regulatory Review | 2022-06-01 | 2022-12-31 | 2022-12-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90041 | Final Commissioning | 2022-07-01 | 2023-01-31 | 2023-01-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90042 | Final Handing Over | 2022-08-01 | 2023-02-28 | 2023-02-28 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90043 | Final Operation Readiness | 2022-09-01 | 2023-03-31 | 2023-03-31 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90044 | Final Project Closeout | 2022-10-01 | 2023-04-30 | 2023-04-30 | On Time
9 | Kaiga Nuclear Power Project | Nuclear Power Plant | Kaiga | Karnataka | 90045 | Final Report Submission | 2022-11-01 | 2023-05-31 | 2023-05-31 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100001 | Project Kickoff | 2022-07-01 | 2022-07-02 | 2022-07-02 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100002 | Site Survey | 2022-07-03 | 2022-07-10 | 2022-07-09 | Delayed | Weather Conditions | Material
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100003 | Feasibility Study | 2022-07-11 | 2022-07-20 | 2022-07-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100004 | Design Phase 1 | 2022-07-21 | 2022-08-10 | 2022-08-08 | Delayed | Resource Availability | Men
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100005 | Design Phase 2 | 2022-08-11 | 2022-08-28 | 2022-08-28 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100006 | Procurement Planning | 2022-08-29 | 2022-09-08 | 2022-09-08 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100007 | Vendor Selection | 2022-09-09 | 2022-09-18 | 2022-09-18 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100008 | Order Placement | 2022-09-19 | 2022-09-25 | 2022-09-25 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100009 | Initial Site Preparation | 2022-09-26 | 2022-10-05 | 2022-10-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100010 | Equipment Delivery | 2022-10-06 | 2022-10-16 | 2022-10-14 | Delayed | Logistic Issues | Material
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100011 | Foundation Work | 2022-10-17 | 2022-10-28 | 2022-10-28 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100012 | Structural Steel Erection | 2022-10-29 | 2022-11-18 | 2022-11-18 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100013 | Mechanical Installation | 2022-11-19 | 2022-12-10 | 2022-12-10 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100014 | Electrical Installation | 2022-12-11 | 2022-12-30 | 2022-12-29 | Delayed | Material Shortage | Material
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100015 | Piping Installation | 2023-01-01 | 2023-01-20 | 2023-01-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100016 | HVAC Installation | 2023-01-21 | 2023-01-30 | 2023-01-30 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100017 | Instrumentation Installation | 2023-01-31 | 2023-02-10 | 2023-02-09 | Delayed | Technical Issues | Machinery
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100018 | Insulation and Painting | 2023-02-11 | 2023-02-20 | 2023-02-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100019 | Pre-commissioning Activities | 2023-02-21 | 2023-02-28 | 2023-02-28 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100020 | Commissioning Phase 1 | 2023-03-01 | 2023-03-10 | 2023-03-10 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100021 | Commissioning Phase 2 | 2023-03-11 | 2023-03-20 | 2023-03-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100022 | Final Inspection | 2023-03-21 | 2023-03-25 | 2023-03-25 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100023 | Project Handover Preparation | 2023-03-26 | 2023-03-30 | 2023-03-30 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100024 | Project Handover | 2023-03-31 | 2023-04-05 | 2023-04-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100025 | Site Demobilization | 2023-04-06 | 2023-04-10 | 2023-04-10 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100026 | Landscaping | 2023-04-11 | 2023-04-20 | 2023-04-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100027 | Final Documentation | 2023-04-21 | 2023-04-30 | 2023-04-30 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100028 | Safety Training | 2023-05-01 | 2023-05-05 | 2023-05-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100029 | Operational Training | 2023-05-06 | 2023-05-15 | 2023-05-15 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100030 | System Integration Testing | 2023-05-16 | 2023-05-25 | 2023-05-25 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100031 | Quality Assurance | 2023-05-26 | 2023-06-05 | 2023-06-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100032 | Regulatory Compliance Check | 2023-06-06 | 2023-06-10 | 2023-06-10 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100033 | Risk Assessment | 2023-06-11 | 2023-06-15 | 2023-06-15 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100034 | Final Adjustments | 2023-06-16 | 2023-06-20 | 2023-06-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100035 | Post-implementation Review | 2023-06-21 | 2023-06-25 | 2023-06-25 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100036 | Stakeholder Meeting | 2023-06-26 | 2023-06-27 | 2023-06-27 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100037 | Feedback Collection | 2023-06-28 | 2023-06-30 | 2023-06-30 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100038 | Process Improvement Planning | 2023-07-01 | 2023-07-05 | 2023-07-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100039 | Implementation of Improvements | 2023-07-06 | 2023-07-15 | 2023-07-15 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100040 | Maintenance Schedule Setup | 2023-07-16 | 2023-07-20 | 2023-07-20 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100041 | Regular Maintenance | 2023-07-21 | 2023-07-30 | 2023-07-30 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100042 | Performance Review | 2023-08-01 | 2023-08-05 | 2023-08-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100043 | Final Report Preparation | 2023-08-06 | 2023-08-10 | 2023-08-10 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100044 | Submission to Authorities | 2023-08-11 | 2023-08-12 | 2023-08-12 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100045 | Regulatory Approval | 2023-08-13 | 2023-08-18 | 2023-08-18 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100046 | Project Closeout | 2023-08-19 | 2023-08-23 | 2023-08-23 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100047 | Knowledge Transfer | 2023-08-24 | 2023-08-30 | 2023-08-30 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100048 | Archiving Documents | 2023-09-01 | 2023-09-05 | 2023-09-05 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100049 | Final Audit | 2023-09-06 | 2023-09-10 | 2023-09-10 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100050 | Project Completion | 2023-09-11 | 2023-09-15 | 2023-09-15 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100051 | Performance Assessment | 2023-09-16 | 2023-09-18 | 2023-09-18 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100052 | Stakeholder Review | 2023-09-19 | 2023-09-21 | 2023-09-21 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100053 | Project Signoff | 2023-09-22 | 2023-09-24 | 2023-09-24 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100054 | Closeout Report | 2023-09-25 | 2023-09-27 | 2023-09-27 | On Time
10 | Cochi Refinery Project | Oil and Gas Refinery | Cochi | Kerala | 100055 | Final Presentation | 2023-09-28 | 2023-10-01 | 2023-09-30 | Delayed | Overall Delays | Men/Material/Machinery
Formulas:
Start Date = [Start Date, row above]
End Date = [End Date, row above]+5
Planned End Date = [Planned End Date, row above]+10